## Sheet1
Project | John Hancock - Coeus Security Updates and KPI Scorecard Frontend Integration 1 Assembly
Review ID | 384446
Review Type | Aggregation
Author | zaixiang
Submission | 516392
Name | Description | Reviewer | Response Type | Status | Comment
Group 1 | General Assembly
Question 1.1.2 | Each minor requirement was implemented correctly as specified in the contest specification.
Reviewer Response 1 | if KSTNormalUser only has "Owner" role, do not assign value for KPI Role. then login as KSTNormalUser, select "KPI ScoreCard Tool". the page is strange, i cannot see any menu, but it display the "Manage Risk Assessment" feature. IMO, it should show messages to user, and do not display the "Manage Risk Assessment" feature. https://www.screencast.com/t/1IEEQ6qPvZZj | zaixiang | Required | Accepted | Fixed
Reviewer Response 2 | if KSTNormalUser has both "Owner" and "KPIUser" role. then login as KSTNormalUser, select "KPI ScoreCard Tool". the page is strange, i can see the menu of KPI app, but it display the "Manage Risk Assessment" feature. https://www.screencast.com/t/3TNYlcu1T | zaixiang | Required | Accepted | Fixed
Reviewer Response 3 | if KSTNormalUser only has "KPIUser" role. then login as KSTNormalUser, select "PCA Tool". the page is strange, i cannot see any menu, but it display the "Key Performance Indicators" feature. | zaixiang | Required | Accepted | Fixed
Reviewer Response 4 | check https://www.screencast.com/t/oSlQH4er, it has layout issue in chrome. | zaixiang | Required | Accepted | Fixed
Reviewer Response 5 | "If a user only has one role (either Coeus or KPI scorecard), then the dropdown at the top of the home page should be disable" currently i always can see two dropdown items. | zaixiang | Required | Accepted | Fixed
Reviewer Response 6 | the "Privacy Incident" section also has UI issue. check https://www.screencast.com/t/dztXWhMKNJ | zaixiang | Required | Accepted | Fixed
Reviewer Response 7 | the "Audit Finding" section also has UI issue. check https://www.screencast.com/t/CYHJ30DILr | zaixiang | Required | Accepted | Fixed
Reviewer Response 8 | http://localhost:8888/index.html#/kpi/editFields in this page, there are many empty areas. check https://www.screencast.com/t/CUYCUWoVKU, a few sections have this issue. | zaixiang | Required | Accepted | Fixed
Reviewer Response 9 | final fix https://apps.topcoder.com/forums//?module=Thread&threadID=897658&start=0 | zaixiang | Required | Accepted | My approach should be correct, I asked in forum for confirmation.
Reviewer Response 11 | (1)login as admin (2)http://localhost:8888/index.html#/kpi/editFields (3)then click the "Key Performance Indicators" menu. check https://www.screencast.com/t/F2pbpiKu, many requests are not for this app. | zaixiang | Required | Accepted | Fixed
Reviewer Response 12 | http://localhost:8888/index.html#/kpi/editFields check the UI Prototype, it should have the submit button. | zaixiang | Required | Accepted | Confirmed in the forum
Reviewer Response 1 | should follow prototype to have more space between options, on Chrome: http://take.ms/CzMAi look more strange on IE11 | fivestarwy | Required | Accepted | Fixed
Reviewer Response 3 | Go to edit businessUnit page, the other sections like "Operational Incident", "Privacy Incident", "Audit Finding" should not be expanded. | fivestarwy | Required | Accepted | Fixed
Reviewer Response 4 | Edit "Business Unit" page, should be able to toggle "Operational Incident", "Privacy Incident", "Audit Finding" by clicking the section header. | fivestarwy | Required | Accepted | Fixed
Reviewer Response 5 | double click one BU entry to edit, the edit field exceed the border, tested on win10, IE11. on chrome, seem the border line move right. http://take.ms/amu7S | fivestarwy | Required | Accepted | Fixed
Reviewer Response 6 | on IE11, the adding input field on the left column exceed the border in all other 3 sections except BU section. http://take.ms/OM1dm | fivestarwy | Required | Accepted | Fixed
Reviewer Response 7 | login as "KST NormalUser", create a scorecard and save as draft, it show: "Your monthly Key Performance Indicators has been submitted." which is the same text as submit the scorecard. | fivestarwy | Required | Accepted | Fixed
Reviewer Response 8 | buttons are hidden if there is erors. http://take.ms/hwu7t | fivestarwy | Required | Accepted | Fixed
Reviewer Response 9 | There is no reporting year "2018" | fivestarwy | Required | Accepted | it was appealed successfully
Reviewer Response 10 | edit page, drag one BU entry to change its order, refresh page, the order is not updated, same for other fields which are dragable. | fivestarwy | Required | Accepted | it is not required. Copilot confirmed that it will be part of next challenge, because backend doesn't support it at all
Reviewer Response 11 | can't add new entry for KPI scorecard settings, "Service Level" and "Threshold" always show error state. http://take.ms/cahJK | fivestarwy | Required | Accepted | it was appealed successfully
Reviewer Response 12 | admin user should not be able to change its own role, just like admin can't inactive himself. | fivestarwy | Required | Accepted | It is existing functionality that is definitely not part of current challenge. I implemented all new requirements for this challenge.
Question 1.1.3 | Does the application handle erroneous input gracefully?
Reviewer Response 1 | When input scorecard, the score percentage value should not exceed 100, should validate the input. | fivestarwy | Required | Accepted | it was appealed successfully
Reviewer Response 2 | in business unit, I can add duplicated "Business Unit", "Volume Type" and "Status", after refresh, they are gone, it seem they are not persisted, but frontend still show it, you should validate the duplicated name, this apply for all adding field input in edit page. http://take.ms/BtiOO | fivestarwy | Required | Accepted | Fixed
Reviewer Response 3 | input all required field in "Data Selection" section, click "Save as Draft", it show popup "Please fill Scores and Volumes for all Key Performance Indicators." it should save information which have already input. | fivestarwy | Required | Accepted | it was appealed successfully